## Slide 1: Contracts for Developments

## Slide 2: Key Players in Development Contracts
Developer/Owner/Client/Employer
Architect/Contract Administrator
Quantity Surveyor
Main Contractor
Sub-contractors
Engineer

## Slide 3: Construction Contracts - Overview

## Slide 4: Examples of Standard Construction Contracts
Standard Form of Building Contract: Private Edition with Quantities (2018 Revision) published by the Construction Industry Council for the Building and Construction Industry in Jamaica (“CIC contract”);
Conditions of Contract for Construction (Red Book) published by the Fédération Internationale des Ingénieurs-Conseils (“FIDIC”)

## Slide 5: Key Provisions in Standard Construction Contracts
Scope of Work
Contract Sum
Payment Schedule
Timelines
Variations
Liability for Defects

## Slide 6: Scope of Work
Defines the work to be carried out, including type of construction to be performed, the required specifications, schedule, materials and goods, the access to and logistics of the site and other critical elements.
Developer has the Architect/Contract Administrator prepare the Drawings and Bills of Quantities showing the work to be done.
Contractor is required to carry out and complete the Works in compliance with the Contract Documents in every respect AND in accordance with the directions and to the reasonable satisfaction of the Architect/Contract Administrator. (Clause 1(1) of CIC contract)

## Slide 7: Variations
Most construction contracts will define what is a “variation” under that contract.
Generally, a variation is an instruction by the employer to alter the works to be performed or an instruction to vary their timing, method or sequence.
Not all instructions will be treated as variations. Disputes have arisen regarding whether the newly instructed work is a variation or a part of the originally contracted scope of works.

## Slide 8: Variations
Variation is specifically defined in Clause 11(2) of the CIC contract as the alteration or modification of the design, quality or quantity of the Works as shown on the Contract Drawings and in the Contract Bills and includes:
  The addition, omission or substitution of any work;
  The alteration of the kind or standard of any of the materials or goods to be used in the Works;
  The removal from the site of any work, materials or goods executed or brought thereon by the Contractor for the purpose of the Works other than work materials or goods which are not in accordance with this Contract.

## Slide 9: Delay and Extension of Time
Under Clause 23 of the CIC contract, the Contractor can in certain circumstances obtain an extension of time to complete the Works if in the opinion of the Architect/Contract Administrator the delay is due to one of the causes specified in the clause.

## Slide 10: Delay and Extension of Time (cont’d)
Force majeure
Exceptionally inclement weather
Loss or damage occasioned by certain natural disasters (except where it is caused by the Contractor’s negligence)

## Slide 11: Delay and Extension of Time (cont’d)
Civil commotion, strike or lockout
National or regional building industry dispute
Instructions issued by the Architect under certain clauses, such as variations
Contractor not receiving the necessary instructions, drawings, details or levels from the Architect in due time

## Slide 12: Delay and Extension of Time (cont’d)
Any act or default of nominated sub-contractors or nominated suppliers
Any act or default of artists, trademen or others engaged by the Employer in other works
Opening up of inspection of any work covered up or testing of any of the work

## Slide 13: Delay and Extension of Time (cont’d)
Contractor’s inability for reasons beyond his control to secure labour, goods, materials and/or equipment essential for the proper carrying out of the work
Compliance with Architect’s instructions regarding antiquities
Failure of Employer to pay full amount certified by the final date for payment

## Slide 14: Delay and Extension of Time (cont’d)
If criteria satisfied, then the Architect shall:
within a reasonable time estimate the length of the delay
make a fair and reasonable extension of time in writing
Contractor still has duty to constantly use his best endeavours to prevent delay and do all that may be reasonably required to the satisfaction of the Architect to proceed with the Works.

## Slide 15: Liability for Defective Work
Contract specifies a Defects Liability Period. Parties are free to agree on a particular period but if none is stated then it is 6 months from the date of the Certificate of Practical Completion of the Works.
Practical Completion triggers the start of the Defects Liability Period. Clause 15(1) of CIC contract stipulates that practical completion shall be when the Architect is of the opinion that the Works or a section of it is completed sufficiently to enable the Employer to utilize it for the purpose for which it was designed.

## Slide 16: Liability for Defective Work (cont’d)
Architect required to specify any defects, shrinkages or other faults which shall appear within the Defects Liability Period in a Schedule of Defects to be provided to the Contractor.
Contractor required to make good these defects, shrinkages or other faults within the Defects Liability Period
Disputes regarding patent vs latent defects: Patent defects are obvious and usually discovered during inspection, whereas latent defects are hidden. Contractor’s liability exposure not limited to the Defects Liability Period.

## Slide 17: Developer/Purchaser Contracts
Escalation is a key provision as it allows for the increase in the cost of the property due to fluctuations in the prices for labour and materials used in the construction project.
Proposed plans and specifications – What exactly is the Developer agreeing to provide the Purchaser with?
Permits and Approvals – What is the Developer approved to build?
Liability for defects also a common point of dispute.
Whether time is of the essence